## Sheet1
Week | Macro planning | Micro | status
1 | Reg File | Coding Verifiyng with a simple test bench(writes and reads from registers) | done
2 | K means core | Do core blocks as shells | done
3 | K means core | finish core blocks as shells Start classification block -first part | done
4 | K means core | Do core blocks as shells Start classification block -second part | done
5 | K means core | New means calculation block
6 | K means core | Convergence check block
7 | K means core | Core controller
8 | K means core | Adding RAM to the core
9 | Integration | Core parts - verifying core with simple test bench
10 | Integration | Integrating reg file to core
11 | Zero order verification | verifying K means top with simple test bench
12 | Zero order verification | verifying K means top with actual data and comparing to matlab
13 | Synthesis & Layout | TBD
14 | Update project report | Pins description section User's instructions Verification section Doing final presentation
15 | Presentation | Submitting the project report